## Estimate Worksheet
Project Estimate: [Project Name]
Total Days (Lower): 9 | Remaining Days (Lower): 6.5
Total Days (Mid): 14 | Remaining Days (Mid): 10.25
Total Days (Upper): 19 | Remaining Days (Upper): 5
Num Sprints (Lower): 0.45 | Remaining Num Sprints (Lower): 0.325
Num Sprints (Mid): 0.7 | Remaining Num Sprints (Mid): 0.5125
Num Sprints (Upper): 0.95 | Remaining Num Sprints (Upper): 0.7
Task | Point | ApplyTestTax | Percentage Complete | Adjusted Point | Days Lower | Day Mid | Days Upper | Days Remain Lower | Days Remaining Mid | Days Remain Upper
Task1 - eg simple text change no tests | 1 | FALSE | 0% | 1 | 1 | 1 | 1 | 1 | 1 | 1
Task2 - with tests | 3 | TRUE | 0% | 5 | 3 | 5.5 | 8 | 3 | 5.5 | 8
Task3 - partially completed already | 5 | TRUE | 50% | 8 | 5 | 7.5 | 10 | 2.5 | 3.75 | 5
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Variables
Variable Table:
| Point | DayMin | DayMax
| 0 | 0 | 0
| 1 | 1 | 1
| 2 | 1 | 2
| 3 | 2 | 5
| 5 | 3 | 8
| 8 | 5 | 10
| 13 | 10 | 15
| 21 | 15 | 30
Number of Devs: | 2
Sprint Length: | 10